## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | System Architecture Design | MUST HAVE | No Dependency | Baby Prasanna | 3- Completed
S1 | S1 | US-001 | Orchestration Flow Design | MUST HAVE | System Architecture Design | Rajeswari | 3- Completed
S1 | S1 | US-001 | Agent Persona Model | MUST HAVE | Orchestration Flow Design | Rajeswari | 3- Completed
S1 | S1 | US-001 | UI Wireframes | SHOULD HAVE | No Dependency | Baby Prasanna | 3- Completed
S2 | S2 | US-002 | Orchestrator Agent (turn order, conversation history, round count) | MUST HAVE | Agent Persona Model | Bhanu | 3- Completed
S2 | S2 | US-002 | AI Agent Reasoning (LLM-based offer generation per persona) | MUST HAVE | Orchestrator Agent | Baby Prasanna | 3- Completed
S2 | S2 | US-002 | Accept / Counter / Reject decision logic | MUST HAVE | AI Agent Reasoning | Dharma | 3- Completed
S2 | S2 | US-002 | Wire negotiation engine together and connect to Start Negotiation button | MUST HAVE | Orchestrator Agent, AI Agent Reasoning, Accept/Counter/Reject Logic | Bhanu, Baby Prasanna, Dharma | 3- Completed
S2 | S2 | US-002 | Testing across all 3 negotiation scenarios | MUST HAVE | Wired negotiation engine | Rajeswari | 3- Completed
S3 | S3 | US-003 | Build Negotiation Arena UI (chat transcript, stance indicators, round metrics) | MUST HAVE | Wired negotiation engine | Rajeswari | 3- Completed
S3 | S3 | US-003 | Human Participant Interface – UI (Practice Mode) | MUST HAVE | Negotiation Arena UI | Dharma | 3- Completed
S3 | S3 | US-003 | Human Participant Interface – backend integration (Practice Mode) | MUST HAVE | Negotiation Arena UI | Baby Prasanna | 3- Completed
S3 | S3 | US-003 | Deadlock Detection Module (stalled-round detection & resolution) | SHOULD HAVE | Orchestrator Agent | Naren | 3- Completed
S3 | S3 | US-003 | Validate Practice Mode across all 3 scenarios | MUST HAVE | Human Participant Interface | Bhanu | 3- Completed
S4 | S4 | US-004 | Build Outcome Screen (agreement terms, concession timeline, objective scores) | MUST HAVE | Negotiation Arena UI | Rajeswari | 3- Completed
S4 | S4 | US-004 | Downloadable negotiation transcript and summary report | COULD HAVE | Outcome Screen | Naren | 3- Completed
S4 | S4 | US-004 | End-to-end testing (both modes, all scenarios, all personality combinations) | MUST HAVE | Outcome Screen | Baby Prasanna | 3- Completed
S4 | S4 | US-004 | Technical documentation, project report & final demonstration prep | MUST HAVE | End-to-end testing | Bhanu, Dharma, Naren, Gayathri | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 170 | 12 | 12 | 10 | 13 | 12 | 14 | 17 | 18 | 15 | 12 | 10 | 10 | 9 | 6
SPRINT 1 BACKLOG
US-001 | 1 | Design System Architecture | 24-07-2026 | 27-07-2026 | Baby Prasanna | Design | 3- Completed | 10 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Define Orchestration Flow | 27-07-2026 | 30-07-2026 | Rajeswari | Design | 3- Completed | 9 | 0 | 0 | 0 | 1 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Build Agent Persona Model | 31-07-2026 | 03-08-2026 | Rajeswari | Design | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 2 | 0 | 0 | 0
US-001 | 4 | Create UI Wireframes | 03-08-2026 | 06-08-2026 | Baby Prasanna | Design | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 2 | 2
SPRINT 2 BACKLOG
US-002 | 1900-01-04 | Orchestrator Agent - turn order, conversation history, round count | 07-08-2026 | 10-08-2026 | Bhanu | Coding | 3- Completed | 10 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 1900-01-05 | AI Agent Reasoning - LLM-based offer generation per persona | 10-08-2026 | 14-08-2026 | Baby Prasanna | Coding | 3- Completed | 12 | 0 | 0 | 0 | 2 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 1900-01-06 | Accept / Counter / Reject decision logic | 13-08-2026 | 16-08-2026 | Dharma | Coding | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 0 | 0 | 0 | 0
US-002 | 1900-01-07 | Wire negotiation engine together + connect Start Negotiation button | 17-08-2026 | 19-08-2026 | Bhanu, Baby Prasanna, Dharma | Integration Test | 3- Completed | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0
US-002 | 1900-01-08 | Testing across all 3 negotiation scenarios | 18-08-2026 | 20-08-2026 | Rajeswari | System Test | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2
SPRINT 3 BACKLOG
US-003 | 1900-01-09 | Build Negotiation Arena UI - chat transcript, stance indicators, round metrics | 21-08-2026 | 25-08-2026 | Rajeswari | Build | 3- Completed | 12 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 1900-01-10 | Human Participant Interface - UI (Practice Mode) | 26-08-2026 | 29-08-2026 | Dharma | Coding | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0
US-003 | 1900-01-11 | Human Participant Interface - backend integration (Practice Mode) | 26-08-2026 | 30-08-2026 | Baby Prasanna | Coding | 3- Completed | 12 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0
US-003 | 1900-01-12 | Deadlock Detection Module - stalled-round detection & resolution | 28-08-2026 | 31-08-2026 | Naren | Coding | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0
US-003 | 1900-01-13 | Validate Practice Mode across all 3 scenarios | 01-09-2026 | 03-09-2026 | Bhanu | System Test | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2
SPRINT 4 BACKLOG
US-004 | 1900-01-14 | Build Outcome Screen - agreement terms, concession timeline, objective scores | 07-09-2026 | 10-09-2026 | Rajeswari | Build | 3- Completed | 10 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 16 | Downloadable negotiation transcript and summary report | 09-09-2026 | 11-09-2026 | Naren | Coding | 3- Completed | 6 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 17 | End-to-end testing - both modes, all scenarios, all personality combinations | 11-09-2026 | 14-09-2026 | Baby Prasanna | System Test | 3- Completed | 10 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 18 | Technical documentation, project report & final demonstration prep | 13-09-2026 | 17-09-2026 | Bhanu, Dharma, Naren, Gayathri | Others | 3- Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 2 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Ambiguity in defining agent boundaries and responsibilities across stakeholders | Discussed with mentor and finalized the System Architecture scope
Sprint 1 | Day 9 | Difficulty modeling distinct personality traits for each stakeholder agent | Reviewed similar negotiation frameworks and refined the Agent Persona Model
Sprint 2 | Day 5 | Turn order and round tracking logic conflicted with concurrent agent responses | Redesigned the Orchestrator Agent to enforce strict sequential turn handling
Sprint 2 | Day 12 | Integrating three independently built modules caused interface mismatches | Held a team integration session to align interfaces before wiring modules together
Sprint 3 | Day 4 | Live stance indicators in the Negotiation Arena UI lagged behind actual negotiation state | Optimized state updates and synced the UI with backend round events
Sprint 3 | Day 10 | Deadlock detection falsely triggered during valid but slow negotiations | Tuned the stalled-round threshold and added dynamic round safety limits
Sprint 4 | Day 3 | Outcome Screen scoring did not match per-agent objective satisfaction correctly | Recalculated objective satisfaction formulas and validated against test scenarios
Sprint 4 | Day 9 | Tight timeline for finishing documentation alongside final testing | Split documentation and testing work across team members to run in parallel

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 24-07-2026 | 06-08-2026 | Baby Prasanna, Rajeswari | Documenting architecture decisions as we make them | Assuming requirements without confirming with the team | Holding design discussions before coding | Finalized System Architecture, Orchestration Flow, Agent Persona Model, and UI Wireframes
2 | Sprint 2 | 07-08-2026 | 20-08-2026 | Bhanu, Baby Prasanna, Dharma, Rajeswari | Writing integration checks earlier in development | Building modules in isolation without checking interfaces | Daily sync on orchestrator and reasoning logic | Completed and wired the Orchestrator Agent, AI reasoning, and Accept/Counter/Reject logic; tested across all 3 scenarios
3 | Sprint 3 | 21-08-2026 | 03-09-2026 | Rajeswari, Dharma, Baby Prasanna, Naren, Bhanu | Testing the UI against real negotiation data earlier | Delaying deadlock edge-case handling till the end | Pairing UI and backend work closely | Delivered the Negotiation Arena UI, Human Participant Interface, and Deadlock Detection Module; validated Practice Mode
4 | Sprint 4 | 07-09-2026 | 17-09-2026 | Rajeswari, Naren, Baby Prasanna, Bhanu, Dharma, Gayathri | Preparing documentation alongside development instead of after | Leaving report writing to the last few days | Splitting testing and documentation tasks in parallel | Built the Outcome Screen and transcript export, completed end-to-end testing, and prepared technical documentation and the final demonstration
5
6
7